## Sheet1
|  | ¦ | ¦ | ¦ | [9 empty] | ¦ | ¦ | ¦
|  | ¦ | ¦ | ¦ | [9 empty] | ¦ | ¦ | ¦
|  | ¦ | ¦ | V | [9 empty] | ¦ | ¦ | V
High-Level Project Schedule |  | 1a | 1b | 2a | 2b | 3a | 3b | 4a | 4b | 5a | 5b | 6a | 6b | 1a | 1b | 2a | 2b | 3a | 3b | 4a | 4b | 5a | 5b | 6a | 6b
|  | 2014-06-19 |  | 2014-06-26 |  | 2014-07-03 |  | 2014-07-10 |  | 2014-07-17 |  | 2014-07-24 |  | 2014-06-19 |  | 2014-06-26 |  | 2014-07-03 |  | 2014-07-10 |  | 2014-07-17 |  | 2014-07-24
|  | PLANNED | [11 empty] | ACHIEVED
|  | 2014-06-19 |  | 2014-06-26 |  | 2014-07-03 |  | 2014-07-10 |  | 2014-07-17 |  | 2014-07-24 |  | 2014-06-19 |  | 2014-06-26 |  | 2014-07-03 |  | 2014-07-10 |  | 2014-07-17 |  | 2014-07-24
TEAM MEMBERS: |  | ¦ | ¦ | [10 empty] | ¦ | ¦
Harischandra, Dilusha |  | ¦ | ¦ | [10 empty] | ¦ | ¦
Niesen, Rob |  | ¦ | ¦ | [10 empty] | ¦ | ¦
Raguay, Emmanuel |  | ¦ | ¦ | [10 empty] | ¦ | ¦
Ulloa, Efren |  | ¦ | ¦ | [10 empty] | ¦ | ¦
Vedula, Lalitha |  | ¦ | ¦ | [10 empty] | ¦ | ¦
|  | ¦ | ¦ | [10 empty] | ¦ | ¦
Description of Task/Milestones | Task Responsibility | [24 empty] | Remarks
WEEKLY TASKS and DOCUMENT revisions | All Team Members | [24 empty] | Review and edit all documents as needed
DIAGRAMS: UseCase, Activity, Sequence, Class | All Team Members | [24 empty] | Planned and Completed, Feedback given
Project Presentation - I | All Team Members |  |  | In Progress | [21 empty] | In Progress
Presentation 2 | All Team Members
Final Presentation | All Team Members
CODING | All Team Members | [24 empty] | data feed started
data retrieval and calculations | Rob
function 1 (temperature) | Dilusha
function 2 (wind) | Emmanuel
function 3 (humidity) | Emmanuel
function 4 (history) | Lalitha
constructing user interface | Efren | [24 empty] | decided on user interface (android app)
TESTING | All Team Members